## Sheet1
| 2016-04-12 | 2016-04-14 | 2016-04-19 | 2016-04-21 | 2016-04-26 | 2016-04-28 | 2016-05-03 | 2016-05-05
Task 1 | bar: 2016-04-12
Task 2 | bar: 2016-04-12
Task 3 | bar: 2016-04-12 to 2016-04-14
Task 4 | bar: 2016-04-12 to 2016-04-14
Task 5 | bar: 2016-04-12 to 2016-04-14
Task 6 | bar: 2016-04-19; 2016-04-26 to 2016-04-28
Task 7 | bar: 2016-04-19 to 2016-04-28
Task 8 | bar: 2016-04-21 to 2016-04-28
Task 9 | bar: 2016-04-21 to 2016-04-28
Task 10 | bar: 2016-04-26 to 2016-04-28
Task 11 | bar: 2016-04-26 to 2016-04-28
Task 12 | bar: 2016-04-26 to 2016-05-03
Task 13 | bar: 2016-04-28 to 2016-05-03
Task 14 | bar: 2016-04-28 to 2016-05-03
Task 15 | bar: 2016-04-28 to 2016-05-03
Task 16 | bar: 2016-04-28 to 2016-05-03
Task 17 | bar: 2016-05-05
Task 18 | bar: 2016-05-05
[9 empty] | SCRUM MASTER | PRODUCT OWNER | UML DESIGNER
Task 1 | 2016-04-12: Form team, decide on roles. | x | x | x | 2hr
Task 2 | 2016-04-12: Form the list of features needed in the sprint backlog. | x | x | x | 2hr
Task 3 | 2016-04-12: Create a set of tasks needed to complete the project | x | x | x | 4hr
Task 4 | 2016-04-12: Estimate the time needed for each task (in blocks of 1hr, 2hr, 4hr, 8hr, 2Days) | x |  |  | 4hr
Task 5 | 2016-04-12: Design the first draft of the UML diagram/model | x | x | x | 4hr
Task 6 | 2016-04-12: Finalise the UML model |  |  | x | 6hr
Task 7 | 2016-04-12: Start working on the code prototype based on the example code |  | x |  | 8hr
Task 8 | 2016-04-12: Start devising unit tests | x | x |  | 6hr
Task 9 | 2016-04-12: Generate working examples of QR codes and directions from reception | x | x |  | 6hr
Task 10 | 2016-04-12: work on the code prototype based on the example code | x | x |  | 4hr
Task 11 | 2016-04-12: run unit tests | x | x |  | 4hr
Task 12 | 2016-04-12: Generate working examples of QR codes and consider timing data from reception |  | x |  | 6hr
Task 13 | 2016-04-12: Add any extra features |  | x |  | 4hr
Task 14 | 2016-04-12: Perform dry run of demo |  | x |  | 4hr
Task 15 | 2016-04-12: Ensure all deliverables (above) have been submitted. |  | x |  | 4hr
Task 16 | 2016-04-12: Commit project to github | x | x |  | 2hr
Task 17 | 2016-04-12: Demo project in lab time | x | x | x | 2hr
Task 18 | 2016-04-12: Task requirements | x |  |  | 2hr